## Slide 1
RetailEdge Corp Architecture Blueprint
Hybrid Cloud — Multi-Cloud Modernization Strategy
Date: 01-Jun-2025
Primary: Neha Gupta, Thomas Mueller
QA: Akira Tanaka
HIGHLY CONFIDENTIAL - FOR COMPANY INTERNAL USE BY AUTHORIZED PERSONNEL ONLY

## Slide 2
Contents
01 — Executive Summary
02 — Current Hybrid Architecture (Azure + On-Prem)
03 — Proposed Multi-Cloud Architecture
04 — Microservices Migration Plan
05 — API Gateway & Integration Layer
06 — CDN & Performance Optimization
07 — Budget & Cost Estimates
08 — Timeline & Milestones
09 — Assumptions & Risks
10 — Operations Support Matrix
11 — Success Criteria
12 — Contacts

## Slide 3
Executive Summary
RetailEdge Corp is a global e-commerce and retail analytics company operating in 12 countries with 500+ retail stores and a high-traffic online platform.
The platform serves 8 million monthly active users with $2.1B annual GMV (Gross Merchandise Value).
Current State:
  Primary workloads on Azure (East US 2, West Europe, Southeast Asia)
  Legacy inventory management system on-premises in Chicago DC
  Google Cloud Platform (GCP) used for ML/AI workloads (BigQuery, Vertex AI)
  Total monthly cloud spend: $95,000/month across all platforms
Key Challenges:
  On-prem inventory system is bottleneck — 8 hour batch sync with cloud
  No unified API gateway — 6 different API management solutions in use
  CDN costs are $18,000/month due to unoptimized caching strategy
  Security policies inconsistent across Azure, GCP, and on-prem
Proposed Transformation:
  Migrate on-prem inventory system to Azure as cloud-native microservices
  Implement unified API gateway (Azure API Management) across all clouds
  Optimize CDN with Azure Front Door + Cloudflare for multi-CDN strategy
  Introduce GCP-to-Azure data pipeline for ML model serving at edge
  Implement unified security with Azure Arc for multi-cloud governance
Target Outcome:
  Inventory sync: Real-time (from 8 hours currently)
  API response time: <50ms globally (from current 200-400ms)
  Cloud spend reduction: 25% savings through optimization
  Single security posture across all environments

## Slide 4
Current Hybrid Architecture — Azure + On-Prem
Azure Environment (Primary — 70% of workloads):
  E-Commerce Platform: AKS cluster (3 regions) running 35 microservices
  Database: Azure SQL Managed Instance (Business Critical tier) for transactional data
  Azure Cosmos DB for product catalog (global distribution, multi-region writes)
  Azure Redis Cache (Premium) for session management and product caching
  Azure Service Bus for order processing queue (avg 500,000 orders/day on peak)
  Azure Functions for order fulfillment event processing
  Azure CDN for static assets (images, JS, CSS) — 15TB egress/month
On-Premises — Chicago DC (Legacy — 15% of workloads):
  Inventory Management System (IMS): Monolithic Java 8 application on WebSphere
  Oracle Database 19c for inventory data (12TB, 500M+ SKU records)
  Batch ETL: Informatica PowerCenter for 8-hourly inventory sync to Azure SQL
  POS Integration Hub: Real-time POS transaction feed from 500+ stores
  Hardware: 8 IBM Power9 servers, IBM FlashSystem storage
GCP Environment (AI/ML — 15% of workloads):
  BigQuery data warehouse (200TB) for retail analytics
  Vertex AI for demand forecasting models (refreshed weekly)
  GCP Dataflow for real-time clickstream processing
  ML model predictions exported to Azure via nightly batch file transfer
Current Pain Points:
  Azure ↔ On-Prem: ExpressRoute 1Gbps, but batch sync creates 8-hour data lag
  Azure ↔ GCP: No direct connectivity, using public internet with VPN
  6 different API gateways: Azure APIM, Kong (on-prem), AWS API GW (legacy), NGINX, Apigee, custom

## Slide 5
Proposed Multi-Cloud Architecture — Target Design
The proposed architecture eliminates the on-prem bottleneck and unifies the multi-cloud environment:
Azure (Primary Platform — 80%):
  AKS v2: Upgraded Kubernetes clusters with KEDA auto-scaling
  New Inventory Microservices (replacing monolith):
    Inventory Query Service (read-optimized, Cosmos DB backend)
    Inventory Update Service (write-optimized, event-sourced)
    Inventory Sync Service (real-time store POS → cloud)
    Stock Allocation Service (order reservation engine)
    Warehouse Management Service (fulfillment orchestration)
  Azure Event Hubs for real-time POS data streaming (replacing batch ETL)
  Azure SQL Hyperscale for transactional data (replacing Managed Instance)
  Azure Cosmos DB (unchanged — global catalog)
GCP (AI/ML Platform — 15%):
  BigQuery (unchanged)
  Vertex AI (unchanged) with new real-time model serving endpoint
  Cloud Interconnect to Azure (direct 10Gbps link via Megaport)
  ML predictions served via gRPC to Azure in real-time (replacing nightly batch)
Multi-Cloud Networking:
  Azure ExpressRoute (10Gbps upgrade) for store connectivity
  Google Cloud Interconnect to Azure via Megaport for GCP ↔ Azure
  Azure Front Door as global entry point for all traffic
Security Unification:
  Azure Arc for multi-cloud governance (Azure + GCP + edge)
  Microsoft Sentinel for SIEM across all environments
  Azure Policy applied uniformly via Arc
  Zero Trust Network Access via Azure Entra ID + Conditional Access

## Slide 6
Microservices Migration Plan — Inventory System
The monolithic Java 8 Inventory Management System will be decomposed into 5 microservices:
Service 1: Inventory Query Service
  Technology: Java 21 + Spring Boot + Cosmos DB (read replicas)
  Traffic: 50,000 queries/second during peak (Black Friday)
  Latency target: <20ms P99
  Pattern: CQRS (reads separated from writes)
Service 2: Inventory Update Service
  Technology: Java 21 + Spring Boot + Azure SQL Hyperscale
  Traffic: 10,000 updates/second during peak
  Pattern: Event Sourcing with Azure Event Hubs
  Every inventory change published as event for downstream consumers
Service 3: Inventory Sync Service (POS → Cloud)
  Technology: Java 21 + Spring Boot + Azure Event Hubs consumer
  Replaces: Informatica batch ETL (8-hour lag → real-time)
  Receives POS transactions from 500+ stores in real-time
  Processes 2M+ POS events/day
Service 4: Stock Allocation Service
  Technology: Java 21 + Spring Boot + Azure Redis Cache
  Handles order-time stock reservation (prevents overselling)
  Supports optimistic locking with Redis distributed locks
Service 5: Warehouse Management Service
  Technology: .NET 8 + Azure Service Bus (existing team expertise)
  Orchestrates fulfillment across 12 warehouses globally
  Integrates with third-party logistics (FedEx, UPS, DHL APIs)
Database Migration:
  Oracle 19c (12TB) → Azure SQL Hyperscale + Cosmos DB
  Oracle-specific PL/SQL procedures rewritten as application logic
  Data migration using Azure Database Migration Service (Oracle → SQL)
  Parallel run: 4 weeks of dual-write (Oracle + Azure) before Oracle decommission

## Slide 7
API Gateway & Integration Layer — Unification
Current API Landscape (fragmented):
  Azure API Management: E-commerce APIs (product, cart, checkout)
  Kong Gateway (on-prem): Inventory APIs (legacy)
  AWS API Gateway: Legacy mobile app APIs (migrated 2 years ago, still active)
  NGINX: Internal microservice routing
  Apigee: Partner APIs (B2B catalog sharing)
  Custom Python Flask API proxy: ML prediction APIs
  Total: 340+ APIs across 6 gateways
Proposed Unified Architecture:
  Azure API Management (Premium tier) as single gateway for ALL APIs
  Self-hosted APIM gateway deployed on AKS for lowest latency
  Self-hosted APIM gateway on GCP GKE for ML API proxying
API Categories (post-unification):
  Customer APIs (150+): Product search, cart, checkout, order tracking
  Partner APIs (45+): B2B catalog, pricing, inventory sharing
  Internal APIs (100+): Admin, analytics, warehouse, fulfillment
  ML APIs (45+): Recommendations, demand forecast, pricing optimization
Key Integration Patterns:
  Synchronous: REST/gRPC for real-time queries (product search, stock check)
  Asynchronous: Azure Event Hubs + Service Bus for order processing, inventory sync
  Streaming: Azure Event Hubs for POS real-time feed + clickstream
  Batch: Azure Data Factory for nightly analytics ETL to BigQuery
Rate Limiting & Throttling:
  Tier 1 (Premium customers): 10,000 req/min
  Tier 2 (Standard): 1,000 req/min
  Tier 3 (Free/Trial): 100 req/min
  DDoS protection via Azure Front Door + WAF

## Slide 8
CDN & Performance Optimization
Current CDN Issues:
  Azure CDN only — single provider, no failover
  Cache hit ratio: 62% (industry benchmark: 85%+)
  Monthly CDN egress: 15TB at $18,000/month
  No image optimization — serving original 4K product images to mobile
  TTFB (Time to First Byte): 180ms average globally
Proposed Multi-CDN Strategy:
  Primary CDN: Azure Front Door Premium (integrated WAF + routing)
  Secondary CDN: Cloudflare Enterprise (failover + edge compute)
  CDN switching logic via Azure Traffic Manager health probes
Performance Optimizations:
  Image optimization: Azure CDN image transformation (WebP/AVIF auto-convert)
  Product images reduced from 4MB → 200KB average (95% reduction)
  Aggressive caching: Product catalog cached for 5 min (vs current 30 sec)
  Stale-while-revalidate header for improved perceived performance
  Edge caching of ML recommendation responses (60-second TTL)
Target Metrics:
  Cache hit ratio: >90% (from 62%)
  TTFB: <50ms globally (from 180ms)
  CDN cost: $8,000/month (from $18,000 — 56% reduction)
  Core Web Vitals: LCP < 1.5s, FID < 50ms, CLS < 0.05
Edge Compute (Future):
  Cloudflare Workers for A/B test routing at edge
  Azure Front Door Rules Engine for personalized caching per region
  Edge-side ML inference for real-time product recommendations

## Slide 9
Budget & Cost Estimates
Category | Current Monthly | Target Monthly | Savings | Notes
Azure Compute (AKS) | $32,000 | $28,000 | $4,000 | KEDA auto-scaling optimization
Azure Databases | $18,000 | $16,500 | $1,500 | Hyperscale + reserved instances
Azure Networking | $8,000 | $10,500 | -$2,500 | 10Gbps ExpressRoute upgrade
Azure CDN/Front Door | $18,000 | $8,000 | $10,000 | Multi-CDN + optimization
GCP (BigQuery+Vertex) | $12,000 | $12,000 | $0 | No change planned
GCP Interconnect | $0 | $2,500 | -$2,500 | New Megaport link
On-Prem Chicago DC | $7,000 | $0 | $7,000 | Fully decommissioned
Security Tools | $3,000 | $4,500 | -$1,500 | Sentinel + Arc added
TOTAL | $98,000 | $82,000 | $16,000 | 16.3% cost reduction

## Slide 10
One-Time Migration Costs
Category | Cost (USD) | Notes
Inventory System Refactoring | $180,000 | 12-week dev effort, 6 engineers
Oracle → Azure SQL Migration | $35,000 | DMS + PL/SQL rewrite
API Gateway Consolidation | $45,000 | 340 APIs migrated to APIM
Network Infrastructure | $25,000 | Megaport + ExpressRoute upgrade
Performance Optimization | $15,000 | CDN setup + image pipeline
Training & Enablement | $12,000 | Multi-cloud training
Contingency (15%) | $46,800 | Buffer
TOTAL | $358,800 | ROI: 22 months at $16K/month savings

## Slide 11
Timeline & Milestones
Phase | Duration | Key Deliverable | Owner
Assessment & Planning | Weeks 1-3 | Architecture blueprint approved | Neha Gupta
API Gateway Consolidation | Weeks 4-12 | 340 APIs on Azure APIM | API Team
Inventory Microservices Dev | Weeks 4-16 | 5 services deployed on AKS | Dev Team
Oracle DB Migration | Weeks 12-18 | Data migrated to Azure SQL | DBA Team
GCP Interconnect Setup | Weeks 6-10 | 10Gbps link active | Network Team
CDN Optimization | Weeks 8-12 | Multi-CDN live, >90% cache hit | Platform Team
On-Prem Decommission | Weeks 18-22 | Chicago DC hardware returned | Infra Team
Security Unification | Weeks 10-20 | Azure Arc + Sentinel active | Security Team
UAT & Go-Live | Weeks 20-24 | Full production cutover | All Teams

## Slide 12
Assumptions & Risks
Item | Type | Impact | Mitigation
Oracle PL/SQL can be rewritten | Assumption | — | Early POC in Week 2
GCP Interconnect provisioning takes 4 weeks | Assumption | — | Order in Week 1
Black Friday traffic spike during migration | Risk | Critical | No cutover Nov 15-Dec 5
Oracle license termination penalties | Risk | High | Legal review before migration
Microservice decomposition defects | Risk | High | 4-week parallel run
All 340 APIs compatible with APIM | Assumption | — | API audit in assessment phase
Store POS systems support real-time streaming | Assumption | — | POS vendor validation
CDN migration causes cache invalidation storm | Risk | Medium | Gradual traffic migration
GCP team supports Cloud Interconnect | Dependency | Medium | Coordination with GCP CSM

## Slide 13
Operations Support Matrix
Service Area | Team | SLA | Coverage
Azure AKS + Compute | Platform Engineering | 99.95% | 24x7
Azure Databases | DBA Team | 99.99% | 24x7
GCP BigQuery + Vertex AI | Data Engineering | 99.9% | Business Hours + On-call
API Gateway (APIM) | API Platform Team | 99.95% | 24x7
CDN & Front Door | Platform Engineering | 99.99% | 24x7
Security (Sentinel + Arc) | SecOps Team | — | 24x7 SOC
Inventory Microservices | Inventory Dev Team | 99.9% | 24x7
Store POS Integration | Retail Tech Team | 99.9% | Store Hours + On-call

## Slide 14
Success Criteria
The modernization will be deemed successful when RetailEdge confirms:
1. Inventory sync is real-time (<5 second lag from POS to cloud) — replacing 8-hour batch.
2. All 340 APIs are served through unified Azure API Management gateway.
3. API response time is <50ms globally (P99) measured from Azure Front Door edge.
4. E-commerce platform handles 100,000 concurrent users during Black Friday without degradation.
5. Cache hit ratio exceeds 90% across multi-CDN setup.
6. CDN monthly cost reduced to <$8,000 (from $18,000).
7. GCP ML predictions served in real-time (<100ms) via Cloud Interconnect.
8. Oracle database fully decommissioned with zero data loss verified.
9. Chicago data center fully decommissioned and hardware returned.
10. Azure Arc governance policies apply uniformly across Azure + GCP.
11. Microsoft Sentinel SIEM active with alerts for all environments.
12. Monthly cloud spend does not exceed $82,000 (+ contingency).
13. Zero production outages during migration period.

## Slide 15
Contacts
Role | Name | Email
Enterprise Architect | Neha Gupta | neha.g@company.com
Cloud Architect | Thomas Mueller | thomas.m@company.com
QA Lead | Akira Tanaka | akira.t@company.com
RetailEdge CTO | Jennifer Park | j.park@retailedge.com
RetailEdge VP Engineering | Carlos Mendez | c.mendez@retailedge.com
Data Platform Lead | Yuki Watanabe | y.watanabe@company.com