## Slide 1
TechNova Solutions Hosting Integration Blueprint
AWS to Azure Migration — Enterprise SaaS Platform
Date: 15-May-2025
Primary: Rajesh Kumar, Priya Malhotra
QA: Suresh Nair
HIGHLY CONFIDENTIAL - FOR COMPANY INTERNAL USE BY AUTHORIZED PERSONNEL ONLY

## Slide 2
Contents
01 — Executive Summary
02 — Current Architecture Overview
03 — Hosting Integration Process & Timelines
04 — Migration Milestones
05 — High Level Migration Plan (AWS → Azure)
06 — Existing Hosting Overview
07 — Inventory and Assessment Summary
08 — Target Reference Architecture
09 — Budget & Cost Estimates
10 — Website Migration Plan
11 — Key Assumptions
12 — Risk and Dependencies
13 — Success Criteria
14 — Operations Support Matrix
15 — Contacts

## Slide 3
Executive Summary
TechNova Solutions operates a multi-tenant SaaS analytics platform serving 200+ enterprise customers globally.
The platform is currently hosted on AWS (us-east-1 and eu-west-1 regions) across 3 AWS accounts.
Post-acquisition, TechNova's hosting infrastructure must be integrated into the parent company's Azure-based GMCS platform.
Key Highlights:
  Total of 47 servers across production, staging, and development environments
  Primary workloads: Real-time analytics engine, data ingestion pipeline, customer portal, and API gateway
  Current monthly hosting cost: $18,500/month on AWS
  Target: Migrate to Azure within 16 weeks with zero downtime for production
  Migration approach: Phased migration — non-prod first, then production cutover
Critical Dependencies:
  TechNova uses AWS-native services (SQS, Lambda, DynamoDB) that need Azure equivalents
  3 third-party integrations (Twilio, Stripe, Salesforce) must be re-validated post-migration
  SOC2 compliance must be maintained throughout migration
  Data residency requirements: EU customer data must remain in EU region

## Slide 4
Current Architecture Overview — Existing Design
TechNova's current architecture follows a microservices pattern on AWS:
Frontend Layer:
  React-based SPA hosted on CloudFront + S3
  Custom domain: app.technova.io with AWS Certificate Manager SSL
  Average 15,000 concurrent users during peak hours
API Layer:
  AWS API Gateway with rate limiting and API key management
  12 microservices running on ECS Fargate (containerized)
  Service mesh using AWS App Mesh for inter-service communication
  Average API response time: 120ms (P95: 280ms)
Data Layer:
  Primary database: Amazon Aurora PostgreSQL (Multi-AZ, db.r5.2xlarge)
  Cache: ElastiCache Redis cluster (3 nodes, cache.r5.large)
  Search: OpenSearch cluster (3 nodes) for full-text search
  Object storage: S3 buckets (12TB total) for raw data and reports
Event Processing:
  AWS SQS for async task queuing (average 50,000 messages/hour)
  AWS Lambda functions (23 functions) for event-driven processing
  Kinesis Data Streams for real-time analytics ingestion
Monitoring & Logging:
  CloudWatch for metrics and alarms
  ELK stack on EC2 for centralized logging
  PagerDuty integration for alerting

## Slide 5
Hosting Integration Process & Timelines
Phase 1: Inventory & Assessment (Weeks 1-2)
  Complete compute and storage inventory across all 3 AWS accounts
  Decide on disposition of each VM, service, and storage resource
  Apply SOC tools and remediate open vulnerabilities
  Document all AWS-native service dependencies
Phase 2: Blueprint & Planning (Weeks 3-4)
  Finalize hosting integration blueprint with Azure equivalents
  Blueprint details retention, decommissioning, and data migration plan
  Map AWS services to Azure equivalents:
    ECS Fargate → Azure Container Apps
    Aurora PostgreSQL → Azure Database for PostgreSQL Flexible Server
    ElastiCache Redis → Azure Cache for Redis
    SQS → Azure Service Bus
    Lambda → Azure Functions
    Kinesis → Azure Event Hubs
    S3 → Azure Blob Storage
Phase 3: Build & Configure (Weeks 5-10)
  Provision Azure landing zone per company standards
  Build destination infrastructure using Terraform IaC
  Configure networking, VPN peering, and firewall rules
  Set up Azure DevOps pipelines for CI/CD migration
Phase 4: Migration & Validation (Weeks 11-14)
  Migrate non-production environments first
  Database migration using Azure Database Migration Service
  Container image migration to Azure Container Registry
  UAT and performance testing
Phase 5: Production Cutover & Stabilization (Weeks 15-16)
  Production cutover with DNS switchover
  48-hour hypercare support
  Decommission legacy AWS resources

## Slide 6
Hosting Integration Milestones
Milestone | Target Date | Owner | Status
Inventory Complete | Week 2 | Rajesh Kumar | In Progress
Blueprint Approved | Week 4 | Priya Malhotra | Not Started
Azure Landing Zone Ready | Week 6 | Cloud Ops Team | Not Started
Non-Prod Migration Complete | Week 10 | Migration Team | Not Started
Database Migration Complete | Week 12 | DBA Team | Not Started
UAT Sign-off | Week 13 | QA Team | Not Started
Production Cutover | Week 15 | All Teams | Not Started
Legacy AWS Decommission | Week 16 | Cloud Ops Team | Not Started
SOC Compliance Verified | Week 16 | Security Team | Not Started

## Slide 7
High Level Migration Plan — AWS to Azure
TechNova has 3 AWS accounts that need to be integrated:
Account 1: Production (Account ID: 556008695729)
  18 ECS services, Aurora PostgreSQL cluster, ElastiCache, OpenSearch
  This is the primary workload — migrates last
  Zero-downtime requirement using blue-green deployment
Account 2: Staging/QA (Account ID: 669412377329)
  Mirror of production at 50% scale
  Used for QA and pre-production validation
  Migrates first as pilot
Account 3: Development (Account ID: 112233445566)
  Developer workstations and CI/CD pipelines
  Jenkins servers, SonarQube, Artifactory
  Migrates to Azure DevOps + GitHub Actions
Migration Approach:
  Containerized services: Re-deploy on Azure Container Apps (minimal changes)
  Databases: Use Azure DMS for online migration with minimal downtime
  Storage: Use AzCopy for S3 → Blob Storage migration (12TB, ~48 hours)
  DNS: Use Traffic Manager for gradual traffic switchover
  Rollback plan: Keep AWS resources active for 2 weeks post-cutover

## Slide 8
Existing Hosting Overview
Internet Traffic Flow:
  Users → CloudFront CDN → API Gateway → ECS Fargate Services → Aurora DB
Public Endpoints:
  https://app.technova.io (Main SaaS application)
  https://api.technova.io (REST API for integrations)
  https://docs.technova.io (Documentation portal — hosted on Netlify, out of scope)
Internal Services:
  Analytics engine: Real-time data processing using Kinesis + Lambda
  Report generator: Batch processing using Step Functions + Lambda
  Notification service: SQS + Lambda + Twilio integration
Authentication:
  AWS Cognito for customer authentication (OAuth2 + SAML)
  15,000+ registered users across 200+ tenant organizations
  MFA enabled for all admin accounts
Remote Access:
  TechNova developers access via AWS SSM Session Manager
  VPN: AWS Client VPN for database access
  IP filtering enabled for admin endpoints

## Slide 9
Inventory and Assessment Summary
Component | Count | Specs | Monthly Cost | Disposition
ECS Services | 18 | Fargate 1vCPU/2GB | $4,200 | Migrate to Container Apps
Aurora PostgreSQL | 1 cluster | db.r5.2xlarge Multi-AZ | $3,800 | Migrate to Azure PostgreSQL
ElastiCache Redis | 3 nodes | cache.r5.large | $1,200 | Migrate to Azure Cache Redis
OpenSearch | 3 nodes | r5.large.search | $1,800 | Migrate to Azure AI Search
S3 Buckets | 8 | 12TB total | $280 | Migrate to Blob Storage
Lambda Functions | 23 | Serverless | $450 | Migrate to Azure Functions
SQS Queues | 12 | Standard queues | $85 | Migrate to Service Bus
API Gateway | 1 | REST + WebSocket | $350 | Migrate to Azure API Management
CloudFront | 2 distributions | Global CDN | $520 | Migrate to Azure Front Door
EC2 (ELK Stack) | 3 | m5.xlarge | $1,100 | Migrate to Azure Monitor + Log Analytics
NAT Gateway | 2 | Multi-AZ | $320 | Azure NAT Gateway
Secrets Manager | 1 | 45 secrets | $15 | Azure Key Vault

## Slide 10
Target Reference Architecture — Proposed Design
The proposed Azure architecture maintains the same microservices pattern with Azure-native services:
Frontend Layer (Proposed):
  Azure Front Door (Global CDN + WAF) replacing CloudFront
  Static assets in Azure Blob Storage with CDN endpoint
  Custom domain: app.technova.io with Azure-managed SSL certificates
API Layer (Proposed):
  Azure API Management (APIM) replacing AWS API Gateway
  18 microservices on Azure Container Apps (serverless containers)
  Dapr sidecar for service-to-service communication replacing App Mesh
  Expected API response time: <100ms (P95: <250ms) — improvement over current
Data Layer (Proposed):
  Azure Database for PostgreSQL Flexible Server (Zone-redundant HA)
  Azure Cache for Redis (Premium tier, 3 nodes)
  Azure AI Search replacing OpenSearch
  Azure Blob Storage (Hot tier for active data, Cool tier for archives)
Event Processing (Proposed):
  Azure Service Bus replacing SQS for reliable messaging
  Azure Functions replacing Lambda for event-driven compute
  Azure Event Hubs replacing Kinesis for real-time streaming
Security & Compliance (Proposed):
  Azure Entra ID replacing Cognito (with SAML/OAuth2 federation)
  Azure Key Vault for secrets management
  Azure Policy for governance enforcement
  Microsoft Defender for Cloud for security monitoring
Monitoring (Proposed):
  Azure Monitor + Application Insights replacing CloudWatch
  Azure Log Analytics replacing ELK stack
  Azure Alerts + PagerDuty integration maintained

## Slide 11
Hosting IT Integration Budget Details
Cost Category | One-Time Cost (USD) | Monthly Recurring (USD) | Notes
Azure Infrastructure (Compute) | — | $5,200 | Container Apps + Functions
Azure Database Services | — | $4,100 | PostgreSQL + Redis + AI Search
Azure Networking | — | $1,200 | Front Door + APIM + VPN + NAT
Azure Storage | — | $350 | Blob Storage (Hot + Cool)
Azure Monitoring | — | $800 | Monitor + Log Analytics + Insights
Migration Tooling (DMS, AzCopy) | $2,500 | — | One-time migration tools
Professional Services (PMI team) | $15,000 | — | Migration execution support
Training & Knowledge Transfer | $3,000 | — | Azure training for TechNova team
Contingency (15%) | $3,075 | $1,747 | Buffer for unexpected costs
TOTAL | $23,575 | $13,397 | Net savings: ~$5,100/month vs AWS

## Slide 12
Website Migration Plan
Primary Application:
  https://app.technova.io — Migrated to Azure Container Apps + Front Door
  DNS CNAME update from CloudFront to Azure Front Door endpoint
  SSL certificate provisioned via Azure Front Door managed certificates
API Endpoint:
  https://api.technova.io — Migrated to Azure API Management
  Existing API keys and rate limits replicated in APIM policies
  Backward compatibility maintained for all v2 and v3 API versions
Documentation Portal:
  https://docs.technova.io — Currently hosted on Netlify
  OUT OF SCOPE for this migration — remains on Netlify
Marketing Landing Pages:
  https://try.technova.io — Hosted on Unbounce
  Decision: DECOMMISSION — marketing team will use company CMS instead
DNS Migration Plan:
  Step 1: Add Azure Front Door CNAME alongside existing CloudFront
  Step 2: Use Traffic Manager for weighted routing (10% Azure → 50% → 100%)
  Step 3: Remove CloudFront distribution after 48 hours of full Azure traffic
  Step 4: Update DNS TTL to 300 seconds before cutover

## Slide 13
Key Assumptions
1. TechNova development team will be available for application-level changes and testing during migration.
2. All containerized services are stateless and can be redeployed without data loss.
3. Database schema is compatible with Azure PostgreSQL Flexible Server without major modifications.
4. Third-party integrations (Twilio, Stripe, Salesforce) do not require IP whitelisting changes.
5. SOC2 compliance evidence can be transferred to Azure Security Center / Defender for Cloud.
6. EU data residency is maintained by deploying EU workloads in Azure West Europe region.
7. Current CI/CD pipelines (Jenkins) will be migrated to Azure DevOps or GitHub Actions.
8. TechNova's existing monitoring dashboards can be recreated in Azure Monitor within 1 week.
9. No application code changes are needed for the migration — only infrastructure and configuration changes.
10. Budget approval for Azure infrastructure costs ($13,397/month) is obtained before Phase 3.
11. Legacy AWS accounts will be retained for 30 days post-migration for rollback purposes.

## Slide 14
Risk and Dependencies
Risk/Dependency | Impact | Probability | Mitigation
Database migration data loss | Critical | Low | Pre-migration backup + DMS validation
Downtime during DNS cutover | High | Medium | Traffic Manager weighted routing
AWS-native service incompatibility | High | Medium | Map all services in blueprint phase
Performance degradation post-migration | Medium | Medium | Load testing before cutover
Third-party integration failures | Medium | Low | Pre-migration API testing
Budget overrun | Medium | Medium | 15% contingency included
Team availability during migration | High | Medium | Dedicated migration window
SOC2 compliance gap during transition | Critical | Low | Parallel compliance monitoring

## Slide 15
Hosting Integration Execution Success Criteria
The project will be deemed successful when TechNova confirms completion of:
1. All 18 microservices are running on Azure Container Apps and serving production traffic.
2. Aurora PostgreSQL data is fully migrated to Azure PostgreSQL with zero data loss verified.
3. All public endpoints (app.technova.io, api.technova.io) resolve to Azure infrastructure.
4. API response times are within 10% of pre-migration baseline (P95 < 280ms).
5. Real-time analytics pipeline processes 50,000+ events/hour on Azure Event Hubs.
6. Authentication (Azure Entra ID) works for all 15,000+ users without password resets.
7. SOC2 compliance evidence is active in Microsoft Defender for Cloud.
8. Azure Monitor dashboards replicate all existing CloudWatch alarms and alerts.
9. Remote access via Azure VPN is tested and working for all developers.
10. Legacy AWS accounts are decommissioned (or scheduled for decommission within 30 days).
11. UAT sign-off from TechNova product team and QA team.
12. Operations RACI agreed and signed by all stakeholders.

## Slide 16
Operations Support Matrix
Service Area | Responsible Team | Support Level | Escalation Path
Azure Infrastructure | Cloud Ops (Parent Co.) | 24x7 | L1 → L2 → Cloud Architect
Application Support | TechNova Dev Team | Business Hours | L1 → Dev Lead → CTO
Database Administration | DBA Team (Parent Co.) | 24x7 | L1 → DBA → Architect
Security & Compliance | InfoSec Team | 24x7 | L1 → SOC → CISO
Networking & Connectivity | Network Ops | 24x7 | L1 → Network Engineer
CI/CD Pipelines | DevOps Team | Business Hours | L1 → DevOps Lead
Third-party Integrations | TechNova Dev Team | Business Hours | L1 → Integration Lead

## Slide 17
Contacts
Role | Name | Email | Phone
PMI Lead | Rajesh Kumar | rajesh.kumar@company.com | +91-98765-43210
Technical Architect | Priya Malhotra | priya.m@company.com | +91-98765-43211
QA Lead | Suresh Nair | suresh.n@company.com | +91-98765-43212
Cloud Ops Lead | Amit Verma | amit.v@company.com | +91-98765-43213
TechNova CTO | David Chen | david.chen@technova.io | +1-415-555-0101
TechNova Dev Lead | Sarah Johnson | sarah.j@technova.io | +1-415-555-0102